## Simple Gantt Chart Template
Individual project gantt chart
Vehicle speed tracking using low level image processing | [15 empty] | 2022-03-10 |  |  |  |  | 2023-02-05
PROJECT NAME | [15 empty] | START DATE |  |  |  |  | END DATE
| Project part | Start Date (planned) | End Date (before first report) | % Completed | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01
| Literature review | 2022-10-03 | 2022-10-24 | 0% | bar: 2022-10-03 to 2022-10-17
| Initial testing and prototyping concepts | 2022-10-03 | 2022-10-31 | 0% | bar: 2022-10-03 to 2022-11-21
| Implementing system at high level | 2022-10-24 | 2022-11-07 | 0% | bar: 2022-10-03 to 2022-11-21
| Determining parts for physical system | 2022-11-07 | 2022-11-14 | 0% | bar: 2022-10-10 to 2022-10-17
| Hardware prototyping/capability testing | 2022-11-07 | 2022-11-28 | 0% | bar: 2023-01-30 to 2023-02-20
| Writing and optimizing code for microcontroller | 2022-11-07 | 2022-12-05 | 0% | bar: 2022-11-21 to 2022-12-05; 2023-01-30 to 2023-02-20
| Gathering data through practical testing | 2022-11-28 | 2022-12-05 | 0% | bar: 2023-01-30 to 2023-02-20
| Writing progress report (max 3000 words) | 2022-11-28 | 2022-12-19 | 0% | bar: 2022-12-05 to 2022-12-12
| Creating speed tracking conversion table | 2022-11-28 | 2022-12-12 | 0% | bar: 2023-01-30 to 2023-02-20
| creating housing for system (optional) | 2023-02-20 | 2023-03-06 | 0% | bar: 2023-02-20 to 2023-02-27
| General system improvements and optionals* | 2023-02-06 | 2023-03-20 | 0% | bar: 2023-02-06 to 2023-03-20
| Writing final report (max 10,000 words) | 2023-03-27 | 2023-05-01 | 0% | bar: 2023-03-27 to 2023-05-01
Break | Chirstmas break | 2022-12-19 | 2022-01-09 | 0% | bar: 2022-12-19 to 2023-01-02
Slowdown | Jan Exam revision | 2023-01-09 | 2023-01-30 | 0%
Break | Easter break | 2023-03-27 | 2023-04-24 | 0% | bar: 2023-03-27 to 2023-04-24
Dates refer to work planned over the week starting with the date.
Important deadlines:
13/12/22 - Progress report due (D1)
02/05/23 - Final report due (D2)
Important milestones:
A: A system for tracking all nesscary elements of an image has been found, work on integrating these methods into a high level system can begin.
B: High level system created, this will be used as the template and golden design for the low level system on the microcontroller.
C: Microcontroller based system has been completed to a level where field testing is possible.
D: Testing data has been collected, I can now delvelop the conversion table.
E: Pixel size to distance conversion table complete, best to complete and include in progress report but prehaps not possible.
F: Work stop point, at this point I will try to close down any extra work and settle on writing the report on the current system.
*This means the compromises, known bugs and issues along with extra features that will be discovered when working on the project. I will use this time to go back and fix these issues and add improvements. this will likely involve going back to previous parts of the project to refine different elements, time spent on this will be reflected in final Gantt chart.
The aim is to create a minimum viable system by the progress report. This would be a basic algorithm and hardware setup that can detect to some degree of accuracy the speed of a passing vehicle using images. This is to allow the more occupied second semester to be spent on less vital aspects of the project.

## ©
© TemplateLab.com