## Simple Gantt Chart Template
SIMPLE GANTT CHART TEMPLATE
Customer Management System (Training Schedule) | [15 empty] | 2019-03-05 |  |  |  |  | 2021-01-28 |  |  |  |  | 2020-11-01
PROJECT NAME | [15 empty] | START DATE |  |  |  |  | END DATE |  |  |  |  | LAST UPDATE DATE
Task ID | Task Name | Start Date | End Date | % Completed | 2020-08-22 | 2020-08-29 | 2020-09-05 | 2020-09-12 | 2020-09-19 | 2020-09-26 | 2020-10-03 | 2020-10-10 | 2020-10-17 | 2020-10-24 | 2020-10-31 | 2020-11-07 | 2020-11-14 | 2020-11-21 | 2020-11-28 | 2020-12-05 | 2020-12-12 | 2020-12-19 | 2020-12-26 | 2021-01-02 | 2021-01-09 | 2021-01-16 | 2021-01-23 | 2021-01-30 | 2021-02-06
11 | Trainings | 2020-08-29 | 2021-01-09 | 50% | bar: 2020-08-29 to 2021-01-09
11a | Training Facilities | 2020-10-24 | 2020-12-12 | 25% | bar: 2020-10-24 to 2020-12-12
11b | Training Material | 2020-10-01 | 2020-10-31 | 100% | bar: 2020-10-03 to 2020-10-31
11c | Identify Trainers | 2020-08-29 | 2020-09-12 | 100% | bar: 2020-08-29 to 2020-09-12
11d | Prepare Trainers | 2020-09-19 | 2020-10-17 | 100% | bar: 2020-09-19 to 2020-10-17
11e | Training Schedule | 2020-09-19 | 2020-11-21 | 70% | bar: 2020-09-19 to 2020-11-21
11f | Identify Participants | 2020-09-26 | 2020-11-28 | 60% | bar: 2020-09-26 to 2020-11-28
11g | Send Invitations | 2020-10-18 | 2020-12-05 | 20% | bar: 2020-10-24 to 2020-12-05
11h | Confirm Attendance | 2020-10-26 | 2020-12-12 | 10% | bar: 2020-10-31 to 2020-12-12
11i | Distribute Materials | 2020-11-07 | 2020-12-19 | 0% | bar: 2020-11-07 to 2020-12-19
11j | Training Sessions | 2020-11-14 | 2020-12-26 | 0% | bar: 2020-11-14 to 2020-12-26
11k | Training Certificate | 2020-11-21 | 2021-01-02 | 0% | bar: 2020-11-21 to 2021-01-02
11l | Evaluate Trainings | 2020-11-28 | 2021-01-09 | 0% | bar: 2020-11-28 to 2021-01-09
Notes: |  |  |  |  | 2020-11-28: Approved By
Training facilities shall be provided by the client. List of participants will be coursed to the client Training Coordinator. Meals and snacks are to be provided by the client. |  |  |  |  | 2021-01-23: mm/dd/yyyy
[19 empty] | PROJECT MANAGER | [7 empty] | DATE

## ©
© TemplateLab.com